## Sheet1
Task | Start Date | Duration (Days) | End Date | Group Members
Democratic Conferencing Tool | 2009-11-09 | 104 | 2010-02-21
Prototype Specification | 2009-11-09 | 2 | 2009-11-11 | Robert, Kit
Prototype Implementation | 2009-11-11 | 7 | 2009-11-18 | Robert
Prototype Testing | 2009-11-18 | 3 | 2009-11-21 | Henry
Prototype Evaluation | 2009-11-18 | 3 | 2009-11-21 | Tammie
Interim Report | 2009-11-09 | 26 | 2009-12-05
Interim Report: The Problem | 2009-11-28 | 6 | 2009-12-04 | William
Interim Report: Background research | 2009-11-09 | 5 | 2009-11-14 | Carl, Kit
Interim Report: Requirements spec. | 2009-11-12 | 5 | 2009-11-17 | Robert
Interim Report: Initial design | 2009-11-12 | 5 | 2009-11-17 | William, Robert, Tammie, Carl
Interim Report: Key implementation decisions | 2009-11-12 | 9 | 2009-11-21 | Robert
Interim Report: Initial implementation/prototyping | 2009-11-12 | 12 | 2009-11-24 | Robert, William
Interim Report: Problems encountered so far | 2009-11-21 | 7 | 2009-11-28 | Group
Interim Report: Time plan | 2009-11-09 | 5 | 2009-11-14 | Henry
Final System: Implementation | 2009-12-01 | 87 | 2010-02-26 | Tammie, Robert
Final System: Testing | 2009-12-21 | 74 | 2010-03-05 | Henry,Carl
Final Report: Updated designs | 2009-12-07 | 28 | 2010-01-04 | Robert, William
Final Report: Discussion on implementation/testing | 2009-12-14 | 21 | 2010-01-04 | Robert, Henry, Carl
Final Report: Summary of what was achieved | 2010-02-15 | 21 | 2010-03-08 | Robert, Billy
Final Report: Reflective comments | 2010-02-15 | 21 | 2010-03-08 | Robert
Final Report: Appendix with testing | 2009-12-21 | 74 | 2010-03-05 | Henry, Carl
Final Report: Appendix with minutes | 2010-02-15 | 14 | 2010-03-01 | Tammie
Formulas:
End Date = [Start Date]+[Duration (Days)]