## Sheet1
Task | Start Date | Duration (Days) | End Date | Group Members | Progress
Final System Design | 2010-02-01 | 41 | 2010-03-14 | Carl, Henry, Tammie
Final System Design: Research existing systems with user-friendly designs for inspiration | 2010-02-01 | 10 | 2010-02-11 | Carl, Tammie | x
Final System Design: Interface designs drawn up on paper | 2010-02-04 | 7 | 2010-02-11 | Carl, Tammie | x
Final System Design: Translate initial paper designs into Photoshop or equivalent image editor | 2010-02-11 | 11 | 2010-02-22 | Carl, Tammie | x
Final System Design: Write mock-ups for help menu | 2010-02-14 | 14 | 2010-02-28 | Henry | -
Final System Design: Translate interface designs into HTML/CSS mock-ups | 2010-02-28 | 14 | 2010-03-14 | Carl, Tammie | -
Final System Design: Project logo design | 2010-03-01 | 20 | 2010-03-21 | Billy, Tammie | -
Final System Implementation | 2010-02-10 | 43 | 2010-03-25 | Henry, Robert, Tammie
Final System Implementation: Help Page design & implementation | 2010-02-18 | 32 | 2010-03-22 | Henry, Robert | x
Final System Implementation: Allowing users to vote | 2010-02-07 | 14 | 2010-02-21 | Robert, Tammie | x
Final System Implementation: Enabling voting results to display | 2010-02-18 | 7 | 2010-02-25 | Robert | x
Final System Implementation: Make the Javascript counter work correctly | 2010-02-15 | 7 | 2010-02-22 | Robert | x
Final System Implementation: Implement confirmation e-mails to be sent upon registering | 2010-02-12 | 10 | 2010-02-22 | Robert | x
Final System Implementation: Reset the vote timer when the voting has finished | 2010-02-05 | 6 | 2010-02-11 | Robert | x
Final System Implementation: Allow the room creator to perform extra actions within the room | 2010-02-15 | 10 | 2010-02-25 | Robert | x
Final System Implementation: Display the results of the voting upon completion | 2010-02-17 | 8 | 2010-02-25 | Robert | x
Final System Implementation: Commenting of all source code | 2010-03-07 | 7 | 2010-03-14 | Robert | -
Final System Implementation: Detailed system messages to be displayed | 2010-03-07 | 7 | 2010-03-14 | Robert | -
Final System Implementation: Testing | 2010-03-08 | 17 | 2010-03-25 | Henry | -
Final Report | 2010-02-08 | 46 | 2010-03-26 | Billy, Carl, Henry, Kit, Robert, Tammie
Final Report: Choose layout and structure the report | 2010-02-08 | 3 | 2010-02-11 | Billy | x
Final Report: Introduction | 2010-02-08 | 7 | 2010-02-15 | Billy | x
Final Report: Condensed existing research | 2010-02-15 | 7 | 2010-02-22 | Billy | x
Final Report: Discussion on implementation of software | 2010-02-25 | 7 | 2010-03-04 | Billy, Carl, Henry, Robert | x
Final Report: Detailed Time Plan | 2010-02-15 | 10 | 2010-02-25 | Billy | x
Final Report: System Walkthrough with screenshots | 2010-03-01 | 24 | 2010-03-25 | Billy, Tammie | -
Final Report: Summary of what was achieved | 2010-03-08 | 14 | 2010-03-22 | Billy | -
Final Report: Reflective comments | 2010-03-10 | 14 | 2010-03-24 | Billy | -
Final Report: Appendix with testing | 2010-03-15 | 10 | 2010-03-25 | Billy, Henry | -
Final Report: Appendix with minutes | 2010-03-15 | 10 | 2010-03-25 | Billy, Tammie | -
Final Report: Additional research | 2010-02-28 | 14 | 2010-03-14 | Billy, Robert | -
Final Report: Technical Documentation | 2010-02-15 | 10 | 2010-02-25 | Billy, Robert | -
Final Report: Executive Summary | 2010-03-22 | 4 | 2010-03-26 | Billy | -
Formulas:
End Date = [Start Date]+[Duration (Days)]