## Sheet1
Task | Start Date | Duration (Days) | End Date | Group Members
Democratic Conferencing Tool | 2009-11-09 | 104 | 2010-02-21
Prototype | 2009-11-09 | 10 | 2009-11-19 | Robert
Specification | 2009-11-09 | 2 | 2009-11-11 | Robert, Kit
Implementation | 2009-11-11 | 7 | 2009-11-18 | Robert
Testing | 2009-11-20 | 1 | 2009-11-21 | Henry
Evaluation | 2009-11-20 | 1 | 2009-11-21 | Tammie
Interim report | 2009-11-09 | 20 | 2009-11-29 | William
Updated and expanded description of the problem to be solved | 2009-11-09 | 20 | 2009-11-29 | William
Background information and research | 2009-11-09 | 20 | 2009-11-29 | Carl, Kit
Requirements specification for the system to be built | 2009-11-09 | 20 | 2009-11-29 | Robert
Initial design of the proposed system and its user interface | 2009-11-09 | 20 | 2009-11-29 | William, Robert, Tammie, Carl
Record of key implementation decisions | 2009-11-09 | 20 | 2009-11-29 | Robert
Results of any initial implementation steps/prototyping | 2009-11-09 | 20 | 2009-11-29 | Robert, William
Discussion of any problems encountered so far | 2009-11-09 | 20 | 2009-11-29 | Group
Time plan for the project | 2009-11-09 | 20 | 2009-11-29 | Henry
Final System | 2009-11-23 | 94 | 2010-02-25 | Robert
Specification | 2009-11-23 | 3 | 2009-11-26 | Robert, Kit
Implementation | 2009-11-26 | 68 | 2010-02-02 | Tammie, Robert
Testing | 2010-02-15 | 16 | 2010-03-03 | Henry,Carl
Final Group Report | 2009-12-07 | 84 | 2010-03-01 | William
Updated design of the system and its user interface | 2009-12-07 | 84 | 2010-03-01 | Robert, William
Discussion on the implementation and testing of the system | 2009-12-07 | 84 | 2010-03-01 | Robert, Henry, Carl
Summary of what was achieved | 2009-12-07 | 84 | 2010-03-01 | Robert, Billy
Reflective comments on the success of the project | 2009-12-07 | 84 | 2010-03-01 | Robert
An appendix giving a description of how the developed system was tested | 2009-12-07 | 84 | 2010-03-01 | Henry, Carl
Minutes from all formal meetings | 2009-12-07 | 84 | 2010-03-01 | Tammie
Formulas:
End Date = [Start Date]+[Duration (Days)]