## Sheet1
Task | Start Date | Duration (Days) | End Date | Group Members
Democratic Conferencing Tool | 2009-11-09 | 137 | 2010-03-26 | Robert, Billy, Henry, Carl, Kit, Tammie
Prototyping | 2009-11-09 | 12 | 2009-11-21 | Robert, Kit, Tammie, Henry
Prototype Specification | 2009-11-09 | 2 | 2009-11-11 | Robert, Kit
Prototype Implementation | 2009-11-11 | 7 | 2009-11-18 | Robert
Prototype Testing | 2009-11-18 | 3 | 2009-11-21 | Henry
Prototype Evaluation | 2009-11-18 | 3 | 2009-11-21 | Tammie
Interim Report | 2009-11-09 | 26 | 2009-12-05 | Robert, Billy, Henry, Carl, Kit, Tammie
Interim Report: The Problem | 2009-11-28 | 6 | 2009-12-04 | Billy
Interim Report: Background research | 2009-11-09 | 5 | 2009-11-14 | Carl, Kit
Interim Report: Requirements spec. | 2009-11-12 | 5 | 2009-11-17 | Robert
Interim Report: Initial design | 2009-11-12 | 5 | 2009-11-17 | Billy, Robert, Tammie, Carl
Interim Report: Key implementation decisions | 2009-11-12 | 9 | 2009-11-21 | Robert
Interim Report: Initial implementation/prototyping | 2009-11-12 | 12 | 2009-11-24 | Robert, Billy
Interim Report: Problems encountered so far | 2009-11-21 | 7 | 2009-11-28 | Tammie
Interim Report: Time plan | 2009-11-09 | 5 | 2009-11-14 | Henry
Final System | 2010-01-25 | 59 | 2010-03-25 | Robert, Tammie, Henry, Carl
Final System Design | 2010-01-25
Final System: Template Coding | 2010-01-25 | 7 | 2010-02-01 | Robert
Final System: Interface Design | 2010-01-28 | 21 | 2010-02-18 | Tammie, Carl
Final System Implementation
Final System: Help Page design & implementation | 2010-02-18 | 32 | 2010-03-22 | Henry, Robert
Final System: Implementation of Voting System | 2010-02-07 | 46 | 2010-03-25 | Tammie, Robert
Final System: Testing | 2010-03-08 | 17 | 2010-03-25 | Henry
Final Report | 2010-02-08 | 46 | 2010-03-26 | Robert, Billy, Henry, Carl, Kit, Tammie
Final Report: Executive Summary | 2010-03-22 | 4 | 2010-03-26 | Billy
Final Report: Introduction | 2010-02-08 | 7 | 2010-02-15 | Billy
Final Report: Condensed existing research | 2010-02-15 | 7 | 2010-02-22 | Billy
Final Report: Additional research | 2010-02-19 | 10 | 2010-03-01 | Billy, Robert
Final Report: Discussion on implementation of software | 2010-01-28 | 21 | 2010-02-18 | Billy, Robert, Henry, Carl
Final Report: Summary of what was achieved | 2010-03-08 | 14 | 2010-03-22 | Billy
Final Report: Reflective comments | 2010-03-10 | 12 | 2010-03-22 | Billy
Final Report: Appendix with testing | 2010-03-15 | 7 | 2010-03-22 | Billy, Henry
Final Report: Appendix with minutes | 2010-03-15 | 7 | 2010-03-22 | Billy, Tammie
Formulas:
End Date = [Start Date]+[Duration (Days)]