## Sheet1
Task | Start Date | Duration (Days) | End Date | Group Members
Democratic Conferencing Tool | 2009-11-09 | 137 | 2010-03-26 | Billy, Carl, Henry, Kit, Robert, Tammie
Prototyping | 2009-11-09 | 12 | 2009-11-21 | Henry, Kit, Robert, Tammie
Prototype Specification | 2009-11-09 | 2 | 2009-11-11 | Kit, Robert
Prototype Implementation | 2009-11-11 | 7 | 2009-11-18 | Robert
Prototype Testing | 2009-11-18 | 3 | 2009-11-21 | Henry
Prototype Evaluation | 2009-11-18 | 3 | 2009-11-21 | Tammie
Interim Report | 2009-11-09 | 26 | 2009-12-05 | Billy, Carl, Kit, Robert, Tammie
Interim Report: Executive Summary | 2009-11-28 | 7 | 2009-12-05 | Billy
Interim Report: Introduction | 2009-11-09 | 7 | 2009-11-16 | Billy
Interim Report: The Problem | 2009-11-28 | 6 | 2009-12-04 | Billy
Interim Report: Background research | 2009-11-09 | 5 | 2009-11-14 | Carl, Kit
Interim Report: Requirements spec. | 2009-11-12 | 5 | 2009-11-17 | Billy, Robert
Interim Report: Initial design | 2009-11-12 | 5 | 2009-11-17 | Billy, Carl, Robert, Tammie
Interim Report: Key implementation decisions | 2009-11-12 | 9 | 2009-11-21 | Billy, Robert, Tammie
Interim Report: Initial implementation/prototyping | 2009-11-12 | 12 | 2009-11-24 | Billy, Robert
Interim Report: Problems encountered so far | 2009-11-21 | 7 | 2009-11-28 | Billy, Tammie
Interim Report: Time plan | 2009-11-09 | 5 | 2009-11-14 | Billy, Henry
Final System Design | 2010-02-01 | 34 | 2010-03-07 | Carl, Henry, Tammie
Final System Design: Research existing systems with user-friendly designs for inspiration | 2010-02-01 | 10 | 2010-02-11 | Carl, Tammie
Final System Design: Interface designs drawn up on paper | 2010-02-04 | 7 | 2010-02-11 | Carl, Tammie
Final System Design: Translate initial paper designs into Photoshop or equivalent image editor | 2010-02-11 | 11 | 2010-02-22 | Carl, Tammie
Final System Design: Translate interface designs into HTML/CSS mock-ups | 2010-02-15 | 13 | 2010-02-28 | Carl, Tammie
Final System Design: Write mock-ups for help menu | 2010-02-10 | 7 | 2010-02-17 | Henry
Final System Implementation | 2010-02-10 | 43 | 2010-03-25 | Henry, Robert, Tammie
Final System Implementation: Help Page design & implementation | 2010-02-18 | 32 | 2010-03-22 | Henry, Robert
Final System Implementation: Allowing users to vote | 2010-02-07 | 14 | 2010-02-21 | Robert, Tammie
Final System Implementation: Enabling voting results to display | 2010-02-18 | 7 | 2010-02-25 | Robert
Final System Implementation: Make the Javascript counter work correctly | 2010-02-15 | 7 | 2010-02-22 | Robert
Final System Implementation: Implement confirmation e-mails to be sent upon registering | 2010-02-12 | 10 | 2010-02-22 | Robert
Final System Implementation: Reset the vote timer when the voting has finished | 2010-02-05 | 6 | 2010-02-11 | Robert
Final System Implementation: Allow the room creator to perform extra actions within the room | 2010-02-15 | 10 | 2010-02-25 | Robert
Final System Implementation: Display the results of the voting upon completion | 2010-02-17 | 8 | 2010-02-25 | Robert
Final System Implementation: Testing | 2010-03-08 | 17 | 2010-03-25 | Henry
Final Report | 2010-02-08 | 46 | 2010-03-26 | Billy, Carl, Henry, Kit, Robert, Tammie
Final Report: Choose layout and structure the report | 2010-02-08 | 3 | 2010-02-11 | Billy
Final Report: Executive Summary | 2010-03-22 | 4 | 2010-03-26 | Billy
Final Report: Introduction | 2010-02-08 | 7 | 2010-02-15 | Billy
Final Report: Condensed existing research | 2010-02-15 | 7 | 2010-02-22 | Billy
Final Report: Additional research | 2010-02-19 | 10 | 2010-03-01 | Billy, Robert
Final Report: Technical Documentation | 2010-02-15 | 10 | 2010-02-25 | Billy, Robert
Final Report: Discussion on implementation of software | 2010-02-25 | 14 | 2010-03-11 | Billy, Carl, Henry, Robert
Final Report: System Walkthrough with screenshots | 2010-03-01 | 24 | 2010-03-25 | Billy, Tammie
Final Report: Summary of what was achieved | 2010-03-08 | 14 | 2010-03-22 | Billy
Final Report: Reflective comments | 2010-03-10 | 14 | 2010-03-24 | Billy
Final Report: Appendix with testing | 2010-03-15 | 10 | 2010-03-25 | Billy, Henry
Final Report: Appendix with minutes | 2010-03-15 | 10 | 2010-03-25 | Billy, Tammie
Final Report: Detailed Time Plan | 2010-02-15 | 10 | 2010-02-25 | Billy
Formulas:
End Date = [Start Date]+[Duration (Days)]